## project
[67 empty] | PCB released to fab | [7 empty] | PCB back for assembly | [45 empty] | Project Demos
Project Planner
[8 empty] | Period Highlight: |  |  |  |  | 25 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT |  | August 22nd | [9 empty] | Sept 1st | [29 empty] | Oct 1st | [30 empty] | Nov 1st | [29 empty] | Dec 1st
ACTIVITY |  | START | DURATION | START | DURATION | COMPLETE |  | PERIODS | [10 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Lead | [5 empty] | Comments | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116
Control unit tear down |  | 2016-09-02 | 2 | 2016-09-02 | 2 | 100%
Component selection |  | 2016-09-14 | 1 | 2016-09-14 | 1 | 100%
Thermistor LUT generation/control panel communication analysis |  | 2016-09-17 | 2 | 0 | 0 | 0%
Schematic Capture |  | 2016-10-06 | 7 | 0 | 0 | 0% | bar: 6 to 12
PCB Layout |  | 2016-10-13 | 7 | 0 | 0 | 0% | bar: 13 to 20
Order PCBs |  | 2016-10-20 | 7 | 0 | 0 | 0% | bar: 20 to 27
Assemble PCBs |  | 2016-10-28 | 4 | bar: 28 to 31
Board Bring-up |  | 2016-11-02 | 4
Control panel communication |  | 2016-09-19 | 9 | 0 | 0 | 0%
Thermal control logic |  | 2016-09-29 | 6 | 0 | 0 | 0% | bar: 2 to 5
HW/SW Integration |  | 2016-11-07 | 11 | 0 | 0 | 0%
Cloud UI Interface |  | 2016-11-19 | 17 | 0 | 0 | 0%
Project Report |  | 2016-12-07 | 5 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%